KB Foundation Management System: Build Plan

Group 8   |   Lecturer in charge: Ms Olorunmola   |   Stakeholder: KB Foundation Team

# 1. Recommended Tech Stack

To hit a 2-week deadline without sacrificing the required features, go with a Django monolith rather than a split Django and React setup:

| Layer | Choice | Why |
| --- | --- | --- |
| Backend | Django (Python) | Built-in auth, password hashing, admin panel, and ORM cut out most of the plumbing work |
| Frontend | Django Templates + Bootstrap 5 | No separate API layer, no CORS/JWT setup, and no context-switching between two codebases. Fastest path to a working, decent-looking UI |
| Database | MySQL | Matches your comfort zone; Django's ORM makes it a drop-in swap from SQLite if needed |
| File uploads | Django FileField (local media folder) | Simple, no cloud storage setup needed for a class project |
| Extras | django-filter, reportlab / browser print-to-PDF | Saves you from hand-rolling filtering and PDF export |

Why not React here: it's the stack you know, but adding a separate frontend means building a REST API (DRF), auth tokens, and two dev servers. That's real time you don't have in 14 days. Django templates get you 90% of the same result for a fraction of the effort. You can always bolt a React frontend on after the deadline if you want it for your portfolio.

# 2. Core Django Apps

- accounts – custom User model with a role field (admin, member, applicant, reviewer), login/registration, RBAC decorators

- donors – Donor and Donation models

- expenditures – Expenditure model with category choices

- scholarships – ScholarshipApplication, Document, ScholarshipRecipient models

- reports – dashboard and report views (aggregations only, no new models)

Key model relationships:

- Donor has a one-to-many relationship with Donation

- ScholarshipApplication (submitted by an applicant User) creates a ScholarshipRecipient on approval

- Document has a foreign key to ScholarshipApplication, so an applicant can upload multiple files: admission letter, school ID, result, etc.

RBAC approach: Django Groups and Permissions (Admin, Member, Reviewer, Applicant groups) plus a simple role_required decorator for view-level restriction. Password hashing is automatic via Django, so no extra work is needed there.

# 3. 14-Day Timeline

| Day | Focus | Deliverable |
| --- | --- | --- |
| 1-2 | Project setup | Django project and apps scaffolded, MySQL connected, custom User model in place before first migration, Git repo, base template with Bootstrap |
| 3-4 | Auth and RBAC | Login/registration for all 4 roles, Groups/permissions wired up, role-based dashboard shells |
| 5-6 | Donor and donation management | Donor CRUD, Donation CRUD, auto-tracked donation history/count per donor, search and filter |
| 7-8 | Expenditure management | Expenditure CRUD by category, expenditure list with filters, category summary |
| 9-10 | Applicant flow | Self-registration, scholarship application form, document upload, my application status page |
| 11 | Review and approval workflow | Reviewer dashboard, approve/reject/under-review actions, auto-creates recipient record on approval |
| 12 | Member and recipient management | Admin CRUD for foundation members (with login creation), recipient list/detail, repeat-recipient flagging, applicant status tracking |
| 13 | Reports and dashboard | Dashboard summary cards, donation/expenditure/recipient reports, remaining search/filter |
| 14 | Testing and polish | Test all 4 roles for access leaks, seed demo data, UI cleanup, prep demo/defense walkthrough |

If your group has 3-4 members, split by app after Day 2 (one person on donors and expenditures, one on scholarships, one on accounts/RBAC and reports) and run those in parallel. That turns this into more like a 10-day build with buffer room.

# 4. Feature Checklist (from the brief)

- Admin / Member login – Days 3-4

- Scholarship applicant registration – Days 9-10

- Donation record, donor profile, and donation history – Days 5-6

- Expenditure management by category – Days 7-8

- Foundation member management – Day 12

- Secure username/password and hashing – Days 3-4 (Django default)

- Role-based access control – Days 3-4

- Scholarship application form and document upload – Days 9-10

- Application review/approval workflow – Day 11

- Scholarship recipient management – Day 12

- Dashboard summary and reports (donation, expenditure, recipient) – Day 13

- Applicant status tracking – Day 12

- Search and filter – woven into Days 5-13

# 5. Risk Notes

- Set the custom User model up on Day 1. Swapping it in later means wiping migrations.

- Keep the approval workflow simple: a status field with choices (pending, under_review, approved, rejected) is enough. Don't over-engineer a state machine.

- File upload validation (type and size limit) is a 15-minute job. Don't skip it, since it's an easy marking point.